## Required_Documents
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Compiled BRN CEP application binder | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | BRN CEP application materials | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | 30 contact-hour / 10-module RN case management course package | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Course/contact-hour map | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Representative course packet | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Instructor/SME evidence where source-backed | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Certificate controls | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Official forms ready for signature/date | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending BRN CEP Approval

## Forms
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Official forms ready for signature | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\03_BRN_CEP_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Yadvir | Ready for signature/date | Human signature/date pending | yes | Before submission | Unbranded and visually unaltered PDF pages.

## Course_Materials
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | 01_BRN_30_CONTACT_HOUR_COURSE_MATERIALS_COMPILED.pdf | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\02_COURSE_MATERIALS\01_BRN_30_CONTACT_HOUR_COURSE_MATERIALS_COMPILED.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | RN Case Management in Home Health: 30 contact hours, 10 modules x 3 contact hours. Uses contact hours as the primary term; no BRN approval claim until CEP/provider metadata is issued.
BRN / RN Case Management CEP | 02_BRN_CONTACT_HOUR_MAP_AND_REPRESENTATIVE_COURSE_PACKET.pdf | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\02_COURSE_MATERIALS\02_BRN_CONTACT_HOUR_MAP_AND_REPRESENTATIVE_COURSE_PACKET.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | RN Case Management in Home Health: 30 contact hours, 10 modules x 3 contact hours. Uses contact hours as the primary term; no BRN approval claim until CEP/provider metadata is issued.
BRN / RN Case Management CEP | 03_BRN_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\02_COURSE_MATERIALS\03_BRN_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | RN Case Management in Home Health: 30 contact hours, 10 modules x 3 contact hours. Uses contact hours as the primary term; no BRN approval claim until CEP/provider metadata is issued.
BRN / RN Case Management CEP | 04_BRN_LMS_BUILD_WORKBOOK.xlsx | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\02_COURSE_MATERIALS\04_BRN_LMS_BUILD_WORKBOOK.xlsx | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | RN Case Management in Home Health: 30 contact hours, 10 modules x 3 contact hours. Uses contact hours as the primary term; no BRN approval claim until CEP/provider metadata is issued.

## Instructor_Evidence
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Vanessa/SME evidence verification | yes | pending | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir | Pending final verification | Evidence currentness/attachment final review | yes if agency requires evidence attached | Before submission | Use only source-backed credentials.

## Signatures_Dates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Authorized signer signature/date | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\03_BRN_CEP_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Authorized signer | Pending | Human signature/date | yes | Before submission | Do not alter form visuals.

## Payment
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | $750 BRN payment/check attachment confirmation | yes | pending | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir | Pending final confirmation | Payment/check human item | yes if required | Before submission | Attach proof/check as agency requires.

## Reviewer_Access
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Reviewer access credentials/instructions | yes | pending | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | LMS admin/Yadvir | Pending final confirmation | Credential/url final verification | yes if reviewer access required | Before/after submission as agency requires | Reviewer page must not advertise public enrollment.

## Certificate_Gates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Certificate gate disabled until agency approval metadata | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\02_COURSE_MATERIALS\03_BRN_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | Moodle admin | Documented | Agency metadata pending | yes for certificate issuance | After approval | No certificate issuance while pending.

## Missing_Items
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | CE coordinator designation | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | Prior California nursing CE provider history answer | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | Vanessa SME/instructor evidence packet final verification/attachment | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | Final legal/privacy sign-off on policy packet | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | Authorized signer signature/date on BRN application | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | $750 payment/check attachment confirmation | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | Transfer completed BRN worksheet into official BRN PDF final verification | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
BRN / RN Case Management CEP | Official primary phone number pending owner confirmation before public catalog/website release | yes | no | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\04_BRN_CEP_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.

## Submission_Log
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Submission confirmation | yes | no | internal records folder | Yadvir | Not submitted | Await final packet submission | no | After submission | Record date, method, confirmation, next expected agency response.