## Required_Documents
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Compiled CNA/CDPH application binder | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | CDPH 192B / online CE provider application materials | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | CDPH 193 / relevant provider/course form materials | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Course list and 12-unit / 24-online-hour course structure | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Instructor/SME evidence where required | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Certificate controls, identity confirmation, interactivity, and final participant statement controls | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Official forms ready for signature/date | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Reviewer access and final verification checklist | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDPH Approval

## Forms
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Official forms ready for signature | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\03_CNA_CDPH_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Yadvir | Ready for signature/date | Human signature/date pending | yes | Before submission | Unbranded and visually unaltered PDF pages.

## Course_Materials
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | 01_CNA_24HR_12_UNIT_COURSE_MATERIALS_COMPILED.pdf | yes | yes | 01_CNA_CDPH_CE_APPLICATION\02_COURSE_MATERIALS\01_CNA_24HR_12_UNIT_COURSE_MATERIALS_COMPILED.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | CNA 24-hour online CE course using CCCCO/NATP Modules 10-17 as the source backbone, delivered as 12 Moodle units.
CNA / CDPH Online CE | 02_CNA_COURSE_MATRIX_AND_SOURCE_CROSSWALK.pdf | yes | yes | 01_CNA_CDPH_CE_APPLICATION\02_COURSE_MATERIALS\02_CNA_COURSE_MATRIX_AND_SOURCE_CROSSWALK.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | CNA 24-hour online CE course using CCCCO/NATP Modules 10-17 as the source backbone, delivered as 12 Moodle units.
CNA / CDPH Online CE | 03_CNA_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | yes | yes | 01_CNA_CDPH_CE_APPLICATION\02_COURSE_MATERIALS\03_CNA_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | CNA 24-hour online CE course using CCCCO/NATP Modules 10-17 as the source backbone, delivered as 12 Moodle units.
CNA / CDPH Online CE | 04_CNA_LMS_BUILD_WORKBOOK.xlsx | yes | yes | 01_CNA_CDPH_CE_APPLICATION\02_COURSE_MATERIALS\04_CNA_LMS_BUILD_WORKBOOK.xlsx | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | CNA 24-hour online CE course using CCCCO/NATP Modules 10-17 as the source backbone, delivered as 12 Moodle units.

## Instructor_Evidence
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Vanessa/SME evidence verification | yes | pending | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir | Pending final verification | Evidence currentness/attachment final review | yes if agency requires evidence attached | Before submission | Use only source-backed credentials.

## Signatures_Dates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Authorized signer signature/date | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\03_CNA_CDPH_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Authorized signer | Pending | Human signature/date | yes | Before submission | Do not alter form visuals.

## Payment
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | No fee identified in final packet | yes | pending | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir | Pending final confirmation | Payment/check human item | yes if required | Before submission | Attach proof/check as agency requires.

## Reviewer_Access
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Reviewer access credentials/instructions | yes | pending | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | LMS admin/Yadvir | Pending final confirmation | Credential/url final verification | yes if reviewer access required | Before/after submission as agency requires | Reviewer page must not advertise public enrollment.

## Certificate_Gates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Certificate gate disabled until agency approval metadata | yes | yes | 01_CNA_CDPH_CE_APPLICATION\02_COURSE_MATERIALS\03_CNA_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | Moodle admin | Documented | Agency metadata pending | yes for certificate issuance | After approval | No certificate issuance while pending.

## Missing_Items
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Authorized signer signature/date on official CDPH forms | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
CNA / CDPH Online CE | 192B pricing / membership fields final verification | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
CNA / CDPH Online CE | Separate mailing-address confirmation if needed on CDPH 193 | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
CNA / CDPH Online CE | Vanessa SME/instructor evidence packet final verification/attachment | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
CNA / CDPH Online CE | Reviewer URL, user ID, and password final confirmation | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
CNA / CDPH Online CE | Official primary phone number pending owner confirmation before public catalog/website release | yes | no | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\04_CNA_CDPH_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.

## Submission_Log
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Submission confirmation | yes | no | internal records folder | Yadvir | Not submitted | Await final packet submission | no | After submission | Record date, method, confirmation, next expected agency response.