## Post_SME_Handoff
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | Vanessa/SME approval documented | yes | no | internal approval record | Vanessa/approved SME | Pending | Course materials not yet approved for implementation | yes | Before build | LMS development may not start until Vanessa Valerio, RN or another approved SME has reviewed and approved the course materials. Internal SME approval is required before Aldrin/Dagny begin Moodle course-shell build, content import, quiz import, learner-access configuration, certificate setup, or production implementation. SME approval does not replace agency approval.
Aldrin/Dagny | Planning-only review | yes | yes | 05_ALDRIN_DAGNY_POST_SME_HANDOFF | Aldrin/Dagny | Allowed | No implementation before SME approval | no | Before SME approval | Review requirements only.
Aldrin/Dagny | Course shell/content/quiz/certificate implementation | yes | no | Moodle environment | Aldrin/Dagny | Blocked | SME and agency approval metadata pending | yes | After approvals | No learner-facing launch until agency approval.