## Required_Documents
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Compiled RCFE/CDSS application binder | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | LIC 9141 vendor application | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Nine LIC 9140 course approval forms | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Vendor and course fee/payment notices | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Current filed 9-course / 27-hour structure | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Vanessa Valerio, RN 788389 instructor evidence where source-backed | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Course materials and dementia block | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Official forms ready for signature/date | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Reviewer access documentation | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no |  | Draft / Pending CDSS/ACS Approval

## Forms
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Official forms ready for signature | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\03_RCFE_CDSS_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Yadvir | Ready for signature/date | Human signature/date pending | yes | Before submission | Unbranded and visually unaltered PDF pages.

## Course_Materials
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | 01_RCFE_9_COURSE_27HR_COURSE_MATERIALS_COMPILED.pdf | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\02_COURSE_MATERIALS\01_RCFE_9_COURSE_27HR_COURSE_MATERIALS_COMPILED.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | Current filed RCFE CDSS/ACS packet: 9 LIC 9140 courses totaling 27 hours. Future 40-hour / 12-module concept is excluded from current submission.
RCFE / CDSS CETP | 02_RCFE_COURSE_MATRIX_AND_DEMENTIA_BLOCK.pdf | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\02_COURSE_MATERIALS\02_RCFE_COURSE_MATRIX_AND_DEMENTIA_BLOCK.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | Current filed RCFE CDSS/ACS packet: 9 LIC 9140 courses totaling 27 hours. Future 40-hour / 12-module concept is excluded from current submission.
RCFE / CDSS CETP | 03_RCFE_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\02_COURSE_MATERIALS\03_RCFE_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | Current filed RCFE CDSS/ACS packet: 9 LIC 9140 courses totaling 27 hours. Future 40-hour / 12-module concept is excluded from current submission.
RCFE / CDSS CETP | 04_RCFE_LMS_BUILD_WORKBOOK.xlsx | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\02_COURSE_MATERIALS\04_RCFE_LMS_BUILD_WORKBOOK.xlsx | SME/Yadvir | Included | SME review pending before LMS build | no for submission, yes for LMS build | Before Moodle build | Current filed RCFE CDSS/ACS packet: 9 LIC 9140 courses totaling 27 hours. Future 40-hour / 12-module concept is excluded from current submission.

## Instructor_Evidence
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Vanessa/SME evidence verification | yes | pending | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir | Pending final verification | Evidence currentness/attachment final review | yes if agency requires evidence attached | Before submission | Use only source-backed credentials.

## Signatures_Dates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Authorized signer signature/date | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\03_RCFE_CDSS_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Authorized signer | Pending | Human signature/date | yes | Before submission | Do not alter form visuals.

## Payment
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | $410 CDSS vendor/course fees confirmation | yes | pending | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir | Pending final confirmation | Payment/check human item | yes if required | Before submission | Attach proof/check as agency requires.

## Reviewer_Access
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Reviewer access credentials/instructions | yes | pending | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | LMS admin/Yadvir | Pending final confirmation | Credential/url final verification | yes if reviewer access required | Before/after submission as agency requires | Reviewer page must not advertise public enrollment.

## Certificate_Gates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Certificate gate disabled until agency approval metadata | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\02_COURSE_MATERIALS\03_RCFE_LMS_RAW_COURSE_CONTENT_FOR_POST_SME_BUILD.pdf | Moodle admin | Documented | Agency metadata pending | yes for certificate issuance | After approval | No certificate issuance while pending.

## Missing_Items
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | LIC 9141 sections 6-10 authorized-representative answers final verification | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Selected California business-authority attachment confirmation | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Vanessa SME/instructor evidence packet final verification/attachment | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Course dates and participant-fee values | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Authorized signer signature/date on LIC 9141 and LIC 9140 forms | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Vendor/course fee payment attachment confirmation | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Live-stream reviewer URL/login/platform final confirmation | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.
RCFE / CDSS CETP | Official primary phone number pending owner confirmation before public catalog/website release | yes | no | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\04_RCFE_CDSS_MISSING_OR_PENDING_SUBMISSION_ITEMS.pdf | Yadvir/owner | Pending | Final human/regulator item | varies | Before submission/public release | See missing/pending PDF.

## Submission_Log
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Submission confirmation | yes | no | internal records folder | Yadvir | Not submitted | Await final packet submission | no | After submission | Record date, method, confirmation, next expected agency response.