## Master_Status
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Application binder | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\01_CNA_CDPH_APPLICATION_BINDER.pdf | Yadvir | Included |  | no |  | CNA 24-hour online CE course using CCCCO/NATP Modules 10-17 as the source backbone, delivered as 12 Moodle units.
CNA / CDPH Online CE | Minimum required submission packet | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\02_CNA_CDPH_MINIMUM_REQUIRED_SUBMISSION_PACKET.pdf | Yadvir | Included |  | no |  | Official form pages preserved as appended PDF pages.
CNA / CDPH Online CE | Official forms ready for signature | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION\03_CNA_CDPH_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Yadvir | Ready for signature/date review | Human signature/date pending | yes if not completed | Before submission | Government forms unbranded and visually unaltered.
CNA / CDPH Online CE | Course materials folder | yes | yes | 01_CNA_CDPH_CE_APPLICATION\02_COURSE_MATERIALS | Yadvir / SME | Included | SME approval pending before LMS build | no for application packet; yes for LMS build | Before Moodle build | LMS development may not start until Vanessa Valerio, RN or another approved SME has reviewed and approved the course materials. Internal SME approval is required before Aldrin/Dagny begin Moodle course-shell build, content import, quiz import, learner-access configuration, certificate setup, or production implementation. SME approval does not replace agency approval.
RCFE / CDSS CETP | Application binder | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\01_RCFE_CDSS_APPLICATION_BINDER.pdf | Yadvir | Included |  | no |  | Current filed RCFE CDSS/ACS packet: 9 LIC 9140 courses totaling 27 hours. Future 40-hour / 12-module concept is excluded from current submission.
RCFE / CDSS CETP | Minimum required submission packet | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\02_RCFE_CDSS_MINIMUM_REQUIRED_SUBMISSION_PACKET.pdf | Yadvir | Included |  | no |  | Official form pages preserved as appended PDF pages.
RCFE / CDSS CETP | Official forms ready for signature | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION\03_RCFE_CDSS_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Yadvir | Ready for signature/date review | Human signature/date pending | yes if not completed | Before submission | Government forms unbranded and visually unaltered.
RCFE / CDSS CETP | Course materials folder | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\02_COURSE_MATERIALS | Yadvir / SME | Included | SME approval pending before LMS build | no for application packet; yes for LMS build | Before Moodle build | LMS development may not start until Vanessa Valerio, RN or another approved SME has reviewed and approved the course materials. Internal SME approval is required before Aldrin/Dagny begin Moodle course-shell build, content import, quiz import, learner-access configuration, certificate setup, or production implementation. SME approval does not replace agency approval.
BRN / RN Case Management CEP | Application binder | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\01_BRN_CEP_APPLICATION_BINDER.pdf | Yadvir | Included |  | no |  | RN Case Management in Home Health: 30 contact hours, 10 modules x 3 contact hours. Uses contact hours as the primary term; no BRN approval claim until CEP/provider metadata is issued.
BRN / RN Case Management CEP | Minimum required submission packet | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\02_BRN_CEP_MINIMUM_REQUIRED_SUBMISSION_PACKET.pdf | Yadvir | Included |  | no |  | Official form pages preserved as appended PDF pages.
BRN / RN Case Management CEP | Official forms ready for signature | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION\03_BRN_CEP_OFFICIAL_FORMS_READY_FOR_SIGNATURE.pdf | Yadvir | Ready for signature/date review | Human signature/date pending | yes if not completed | Before submission | Government forms unbranded and visually unaltered.
BRN / RN Case Management CEP | Course materials folder | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\02_COURSE_MATERIALS | Yadvir / SME | Included | SME approval pending before LMS build | no for application packet; yes for LMS build | Before Moodle build | LMS development may not start until Vanessa Valerio, RN or another approved SME has reviewed and approved the course materials. Internal SME approval is required before Aldrin/Dagny begin Moodle course-shell build, content import, quiz import, learner-access configuration, certificate setup, or production implementation. SME approval does not replace agency approval.
Catalog/Website | Official primary phone number | yes | no | 00_START_HERE/03_CE_CATALOG_ADDENDUM_AND_WEBSITE_UPDATE_GUIDE.pdf | Owner confirmation | Pending owner confirmation | official primary phone number must be selected before public catalog/website release | yes for public release | Before website/catalog release | Known inconsistency: (650) 449-6706/support@ci-ion.com vs (408) 443-3026.

## CNA_CDPH
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
CNA / CDPH Online CE | Compiled CNA/CDPH application binder | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | CDPH 192B / online CE provider application materials | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | CDPH 193 / relevant provider/course form materials | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Course list and 12-unit / 24-online-hour course structure | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Instructor/SME evidence where required | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Certificate controls, identity confirmation, interactivity, and final participant statement controls | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Official forms ready for signature/date | yes | pending final human verification | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Reviewer access and final verification checklist | yes | pending final human verification | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Authorized signer signature/date on official CDPH forms | yes | pending final human verification | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | 192B pricing / membership fields final verification | yes | pending final human verification | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Separate mailing-address confirmation if needed on CDPH 193 | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Vanessa SME/instructor evidence packet final verification/attachment | yes | pending final human verification | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Reviewer URL, user ID, and password final confirmation | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDPH Approval
CNA / CDPH Online CE | Official primary phone number pending owner confirmation before public catalog/website release | yes | yes | 01_CNA_CDPH_CE_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDPH Approval

## RCFE_CDSS
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
RCFE / CDSS CETP | Compiled RCFE/CDSS application binder | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | LIC 9141 vendor application | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Nine LIC 9140 course approval forms | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Vendor and course fee/payment notices | yes | pending final human verification | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Current filed 9-course / 27-hour structure | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Vanessa Valerio, RN 788389 instructor evidence where source-backed | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Course materials and dementia block | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Official forms ready for signature/date | yes | pending final human verification | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Reviewer access documentation | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | LIC 9141 sections 6-10 authorized-representative answers final verification | yes | pending final human verification | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Selected California business-authority attachment confirmation | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Vanessa SME/instructor evidence packet final verification/attachment | yes | pending final human verification | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Course dates and participant-fee values | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Authorized signer signature/date on LIC 9141 and LIC 9140 forms | yes | pending final human verification | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Vendor/course fee payment attachment confirmation | yes | pending final human verification | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Live-stream reviewer URL/login/platform final confirmation | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval
RCFE / CDSS CETP | Official primary phone number pending owner confirmation before public catalog/website release | yes | yes | 02_RCFE_CDSS_CETP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending CDSS/ACS Approval

## BRN_CEP
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
BRN / RN Case Management CEP | Compiled BRN CEP application binder | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | BRN CEP application materials | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | 30 contact-hour / 10-module RN case management course package | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Course/contact-hour map | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Representative course packet | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Instructor/SME evidence where source-backed | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Certificate controls | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Official forms ready for signature/date | yes | pending final human verification | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Included |  | no | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | CE coordinator designation | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Prior California nursing CE provider history answer | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Vanessa SME/instructor evidence packet final verification/attachment | yes | pending final human verification | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Final legal/privacy sign-off on policy packet | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Authorized signer signature/date on BRN application | yes | pending final human verification | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | $750 payment/check attachment confirmation | yes | pending final human verification | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Transfer completed BRN worksheet into official BRN PDF final verification | yes | pending final human verification | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval
BRN / RN Case Management CEP | Official primary phone number pending owner confirmation before public catalog/website release | yes | yes | 03_BRN_CARE_MANAGER_CEP_APPLICATION\01_APPLICATION_SUBMISSION | Yadvir | Pending | Final human/regulator item | yes if required field is unresolved | Before submission | Draft / Pending BRN CEP Approval

## Catalog_Website
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
Catalog/Website | Contact information consistency | yes | no | 00_START_HERE/03_CE_CATALOG_ADDENDUM_AND_WEBSITE_UPDATE_GUIDE.pdf | Owner confirmation | Pending owner confirmation | official primary phone number must be selected before public catalog/website release | yes | Before public release | Do not guess official primary phone number.

## Vanessa_SME_Review
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | Vanessa/approved SME review | yes | no | 05_ALDRIN_DAGNY_POST_SME_HANDOFF/01_POST_SME_MOODLE_BUILD_HANDOFF_READ_ME.pdf | Vanessa/approved SME | Pending | Internal educational/clinical approval required before LMS build | yes for LMS development | Before Aldrin/Dagny build | LMS development may not start until Vanessa Valerio, RN or another approved SME has reviewed and approved the course materials. Internal SME approval is required before Aldrin/Dagny begin Moodle course-shell build, content import, quiz import, learner-access configuration, certificate setup, or production implementation. SME approval does not replace agency approval.

## Aldrin_Dagny_Handoff
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | Planning only before SME approval | yes | yes | 05_ALDRIN_DAGNY_POST_SME_HANDOFF | Aldrin/Dagny | Hold active | SME approval not documented | yes for implementation | After SME approval | No course-shell build/content import before SME approval.

## Moodle_Requirements
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
Moodle | Requirements-only PDF | yes | yes | 04_MOODLE_IMPLEMENTATION_REQUIREMENTS/01_MOODLE_SELF_HOST_IMPLEMENTATION_REQUIREMENTS_ONLY.pdf | Moodle admin | Included | Technical admin final verification still required | no for packet; yes before production | Before implementation | Full Moodle source folder not duplicated.

## Missing_Items
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | No missing application-submission docs identified | yes | yes | lane missing/pending PDFs | Yadvir | Human items pending | Signature/date/payment/reviewer/access metadata remain | varies | Before submission | Build-remediable outputs generated.

## Deficiency_Response_Log
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
lane | deficiency notice | yes | no | internal records folder | assigned owner | Not started | Create item when agency notice arrives | yes if agency requires response | Agency due date | Preserve original and corrected versions; do not update public approval claims until issued.

## Approval_Metadata
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | Agency approval/provider/course metadata | yes | no | agency approval letter/metadata | Yadvir | Pending agency approval | Regulator-only item | yes for public claims/certificates | After approval issued | No learner-facing approval claim before metadata.

## Certificate_Gates
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | Certificates disabled until approval metadata | yes | yes | Moodle requirements + lane course materials | Moodle admin | Gate documented | Agency metadata pending | yes for certificate issuance | After approval | BRN uses contact hours, not CEUs.

## Final_QA
lane | item | required yes/no | included yes/no | file path | owner | status | pending reason | submission blocker yes/no | due date | notes
All lanes | Clean folder hygiene validation | yes | yes | GOOGLE_DRIVE_UPLOAD_END_USER_PACKET_CLEAN | Builder | Pass pending final script |  | yes | June 09, 2026 | Only PDF/XLSX expected.