## Dashboard
CNA Recertification Executive Task Tracker
Status | Count | Priority | Count | Gate Status
Not Started |  | P0 Blocker |  | Execution may continue internally; production/certificate/approval claims remain blocked.
In Progress |  | P1 High
Drafted |  | P2 Medium
Complete |  | P3 Low
Needs Source Repair
Needs SME Review
Needs Compliance Review
Needs Legal/CDPH Review
Needs App Verification
Needs Owner Decision
Blocked
Deferred
Not Applicable

## Critical Path
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-001 | Source Evidence | P0 Blocker | High | Needs Source Repair | Yes | Resolve CCCCO/source repair evidence | Survey evidence + ContentV2 gaps | 72 mapped objectives; 7 source repair | Unresolved CCCCO gaps | Repair M03 and under-depth objectives | Source Evidence | SME | Local source docs | Source index | June 3, 2026 | June 3, 2026
CP-002 | ContentV2 / Time Depth | P1 High | High | Needs Compliance Review | No | Close time-depth gap with source-backed expansion | TIME_DEPTH_AUDIT.md | 447.12 active-learning min estimate | Under-depth lessons | Expand without padding | Instructional Designer | Compliance | Source Evidence | Time-depth audit | June 3, 2026 | June 3, 2026
CP-003 | Assessment / Exam | P1 High | High | Needs SME Review | No | Protect final exam keys and flagged questions | Final assessment map | 50-question pool; keys internal-only | Answer-key exposure | Review app final-result boundaries | Assessment Lead | QA / SME | ContentV2 | App QA | June 3, 2026 | June 3, 2026
CP-004 | Certificate Gate | P0 Blocker | Critical | Blocked | Yes | Obtain approval metadata, wording, affidavit method | Certificate reconciliation | No approval artifacts inspected | Improper certificate issuance | Collect written approvals | Program Owner / Legal | Compliance / CDPH | Approval evidence | Gate reconciliation | June 3, 2026 | June 3, 2026
CP-005 | Optional Clinical Support | P1 High | High | Needs Compliance Review | No | Verify non-credit non-gating separation | Optional clinical reconciliation | Support pathway only | Clinical-credit confusion | Run QA-02 and review labels | Compliance | QA | App runtime | QA evidence | June 3, 2026 | June 3, 2026
CP-006 | App / QA | P1 High | High | Needs App Verification | No | Run standalone MVP browser verification | App crosswalk | Files present; not runtime-tested | Route/content mismatch | Run app QA after evidence closure | App Engineer | QA / Compliance | ContentV2 package | Browser evidence | June 3, 2026 | June 3, 2026
CP-007 | Audit / Reconciliation | P1 High | Medium | Needs Owner Decision | No | Resolve 59 undocumented URL rows | URL evidence register | 162 URLs classified | Missing Drive evidence | Re-export failed docs and decide skipped media/folder | Packaging | Program Owner | Drive access | URL register | June 3, 2026 | June 3, 2026
CP-008 | Leadership | P0 Blocker | Critical | Needs Owner Decision | Yes | Complete Dee approval gate only after P0 closures | Go/no-go blockers | P0 open | Premature pilot decision | Review after QA and approvals | Dee Bustos | Compliance / Legal | P0 closure | Approval record | June 3, 2026 | June 3, 2026

## Master Task Tracker
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-001 | Source Evidence | P0 Blocker | High | Needs Source Repair | Yes | Resolve CCCCO/source repair evidence | Survey evidence + ContentV2 gaps | 72 mapped objectives; 7 source repair | Unresolved CCCCO gaps | Repair M03 and under-depth objectives | Source Evidence | SME | Local source docs | Source index | June 3, 2026 | June 3, 2026
CP-002 | ContentV2 / Time Depth | P1 High | High | Needs Compliance Review | No | Close time-depth gap with source-backed expansion | TIME_DEPTH_AUDIT.md | 447.12 active-learning min estimate | Under-depth lessons | Expand without padding | Instructional Designer | Compliance | Source Evidence | Time-depth audit | June 3, 2026 | June 3, 2026
CP-003 | Assessment / Exam | P1 High | High | Needs SME Review | No | Protect final exam keys and flagged questions | Final assessment map | 50-question pool; keys internal-only | Answer-key exposure | Review app final-result boundaries | Assessment Lead | QA / SME | ContentV2 | App QA | June 3, 2026 | June 3, 2026
CP-004 | Certificate Gate | P0 Blocker | Critical | Blocked | Yes | Obtain approval metadata, wording, affidavit method | Certificate reconciliation | No approval artifacts inspected | Improper certificate issuance | Collect written approvals | Program Owner / Legal | Compliance / CDPH | Approval evidence | Gate reconciliation | June 3, 2026 | June 3, 2026
CP-005 | Optional Clinical Support | P1 High | High | Needs Compliance Review | No | Verify non-credit non-gating separation | Optional clinical reconciliation | Support pathway only | Clinical-credit confusion | Run QA-02 and review labels | Compliance | QA | App runtime | QA evidence | June 3, 2026 | June 3, 2026
CP-006 | App / QA | P1 High | High | Needs App Verification | No | Run standalone MVP browser verification | App crosswalk | Files present; not runtime-tested | Route/content mismatch | Run app QA after evidence closure | App Engineer | QA / Compliance | ContentV2 package | Browser evidence | June 3, 2026 | June 3, 2026
CP-007 | Audit / Reconciliation | P1 High | Medium | Needs Owner Decision | No | Resolve 59 undocumented URL rows | URL evidence register | 162 URLs classified | Missing Drive evidence | Re-export failed docs and decide skipped media/folder | Packaging | Program Owner | Drive access | URL register | June 3, 2026 | June 3, 2026
CP-008 | Leadership | P0 Blocker | Critical | Needs Owner Decision | Yes | Complete Dee approval gate only after P0 closures | Go/no-go blockers | P0 open | Premature pilot decision | Review after QA and approvals | Dee Bustos | Compliance / Legal | P0 closure | Approval record | June 3, 2026 | June 3, 2026

## Module Status
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
Module | Title | Minutes | Lessons | Status | Key Source | Review Flag | Next Action
M00 | Orientation and Compliance Boundaries | 30 | 5 | Drafted | Unified Blueprint; Content syllabus | Legal/CDPH copy review | Confirm acknowledgements and no-PHI language
M01 | Infection Control and PPE | 90 | 6 | Needs SME Review | Legacy CNA-CE draft + scattered CCCCO refs | No dedicated NATP 10-17 source | SME/source review and source-backed expansion
M02 | Resident Rights, Abuse Prevention, and Boundaries | 120 | 5 | In Progress | CCCCO/NATP Module 17 | Under-depth expansion | Expand partial objectives from source
M03 | Dementia, Communication, and Respectful Care | 120 | 5 | Needs Source Repair | CCCCO/NATP Modules 13, 16 | Sensitive content and truncated source | Repair M03/L03-L05 from CCCCO M16 and SME review
M04 | Mobility, Falls, and Workplace Safety | 120 | 5 | In Progress | CCCCO/NATP Modules 12, 14 | No hands-on competency claim | Expand source-backed safety/restorative content
M05 | Nutrition, Skin Integrity, Vital Signs | 120 | 5 | Needs SME Review | CCCCO/NATP Modules 10, 11, 13 | Pressure-injury scope review | SME review and CNA-scope wording check
M06 | Documentation, Reporting, PHI Avoidance, and Scope | 90 | 5 | In Progress | CCCCO/NATP Module 15 | PHI and scope controls | Confirm no PHI free text and expand source-backed content
M07 | Final Review, Exam/Test, Affidavit | 30 | 5 | Needs Legal/CDPH Review | All modules; final assessment map | Affidavit/certificate approval | Approve final wording and keep certificate disabled

## Source Evidence
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-001 | Source Evidence | P0 Blocker | High | Needs Source Repair | Yes | Resolve CCCCO/source repair evidence | Survey evidence + ContentV2 gaps | 72 mapped objectives; 7 source repair | Unresolved CCCCO gaps | Repair M03 and under-depth objectives | Source Evidence | SME | Local source docs | Source index | June 3, 2026 | June 3, 2026

## ContentV2 - Time Depth
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-002 | ContentV2 / Time Depth | P1 High | High | Needs Compliance Review | No | Close time-depth gap with source-backed expansion | TIME_DEPTH_AUDIT.md | 447.12 active-learning min estimate | Under-depth lessons | Expand without padding | Instructional Designer | Compliance | Source Evidence | Time-depth audit | June 3, 2026 | June 3, 2026

## Assessment - Exam
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-003 | Assessment / Exam | P1 High | High | Needs SME Review | No | Protect final exam keys and flagged questions | Final assessment map | 50-question pool; keys internal-only | Answer-key exposure | Review app final-result boundaries | Assessment Lead | QA / SME | ContentV2 | App QA | June 3, 2026 | June 3, 2026

## Certificate Gate
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-004 | Certificate Gate | P0 Blocker | Critical | Blocked | Yes | Obtain approval metadata, wording, affidavit method | Certificate reconciliation | No approval artifacts inspected | Improper certificate issuance | Collect written approvals | Program Owner / Legal | Compliance / CDPH | Approval evidence | Gate reconciliation | June 3, 2026 | June 3, 2026

## Optional Clinical Support
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-005 | Optional Clinical Support | P1 High | High | Needs Compliance Review | No | Verify non-credit non-gating separation | Optional clinical reconciliation | Support pathway only | Clinical-credit confusion | Run QA-02 and review labels | Compliance | QA | App runtime | QA evidence | June 3, 2026 | June 3, 2026

## App - QA
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-006 | App / QA | P1 High | High | Needs App Verification | No | Run standalone MVP browser verification | App crosswalk | Files present; not runtime-tested | Route/content mismatch | Run app QA after evidence closure | App Engineer | QA / Compliance | ContentV2 package | Browser evidence | June 3, 2026 | June 3, 2026

## Audit - Reconciliation
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-007 | Audit / Reconciliation | P1 High | Medium | Needs Owner Decision | No | Resolve 59 undocumented URL rows | URL evidence register | 162 URLs classified | Missing Drive evidence | Re-export failed docs and decide skipped media/folder | Packaging | Program Owner | Drive access | URL register | June 3, 2026 | June 3, 2026

## Google Drive Packaging
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
CP-007 | Audit / Reconciliation | P1 High | Medium | Needs Owner Decision | No | Resolve 59 undocumented URL rows | URL evidence register | 162 URLs classified | Missing Drive evidence | Re-export failed docs and decide skipped media/folder | Packaging | Program Owner | Drive access | URL register | June 3, 2026 | June 3, 2026

## Glossary
ID | Domain | Priority | Severity | Status | Blocker | Task / Expected Item | Evidence Source | Current Evidence | Gap / Risk | Required Action | Owner Role | Reviewer Role | Dependency | Verification File / Command | Date Opened | Date Updated | Notes
Term | Definition
Optional Clinical Support | Optional, non-credit, non-gating support pathway; not clinical-hour credit.
Active-Time Validation | Validated evidence that active participation meets time requirements; Moodle logs alone are insufficient.
P0 Blocker | Must be resolved before production/pilot clearance or certificate action.